## Summary
Agentic Workflow Backlog for PM Review | Agentic Workflow Backlog for PM Review | Agentic Workflow Backlog for PM Review | Agentic Workflow Backlog for PM Review | Agentic Workflow Backlog for PM Review | Agentic Workflow Backlog for PM Review
Epic | Story Count |  | Metric | Value
DS | 0 |  | Total Stories | 8
Backend | 3 |  | Total Spikes | 4
UI | 0 |  | High Priority Items | 7
Product | 1
DS Exploration | 4

## Epics
Epic ID | Epic Name | Area | Purpose | Included Work
EPIC-DS | DS | Data Science | All Data Science stories | Model runtime, framework, experimentation, evaluation, workflow logic
EPIC-BE | Backend | Engineering | All engineering work | Service integration, runtime integration, performance, APIs, backend implementation
EPIC-UI | UI | User Interface | User interface work | Front-end features, configuration screens, workflow management UX
EPIC-PROD | Product | Product Management | Product manager tasks | Approvals, requirements, roadmap, stakeholder alignment
EPIC-DSX | DS Exploration | Spike / Exploration | Spike stories to achieve the objective | Proofs of concept, benchmarks, feasibility studies, legacy comparisons

## Stories
Story ID | Epic ID | Epic | Story Type | Story Title | Description | Acceptance Criteria | Priority | Status | Owner | Dependencies | Notes
STORY-001 | EPIC-DSX | DS Exploration | Spike | Apply Stellar Llama 70B model and measure improvement vs legacy model | Run a spike using the Stellar Llama 70B model against the current legacy baseline and document measurable improvement. | Benchmark completed; comparison documented against legacy model; results shared with stakeholders. | High | Not Started |  | Legacy model baseline | Mapped to DS Exploration because it is a spike.
STORY-002 | EPIC-DSX | DS Exploration | Spike | Apply R2D2 + Gemini 2.5 model and measure improvement vs legacy model | Run a spike using the R2D2 workflow with Gemini 2.5 and compare output quality and performance against the legacy baseline. | Evaluation completed; delta vs legacy documented; recommendation captured. | High | Not Started |  | Legacy model baseline | Mapped to DS Exploration because it is a spike.
STORY-003 | EPIC-DSX | DS Exploration | Spike | Build a RAG pipeline and measure improvement vs legacy model | Implement a retrieval-augmented generation pipeline and compare accuracy and user value relative to the legacy model. | RAG prototype built; benchmark results documented; recommendation recorded. | High | Not Started |  | Knowledge sources / baseline metrics | Mapped to DS Exploration because it is a spike.
STORY-004 | EPIC-DSX | DS Exploration | Spike | Assess support for existing RASA library | Evaluate feasibility and approach to support the existing RASA library within the proposed solution architecture. | Feasibility findings documented; constraints and recommendation shared. | Medium | Not Started |  | RASA codebase access | Originally described as a backend spike; tracked under DS Exploration to preserve spike epic structure.
STORY-005 | EPIC-BE | Backend | Story | Call the model from the existing codebase | Integrate the selected model invocation path into the existing codebase without full rewrite. | Existing codebase can successfully invoke the target model end to end in a test environment. | High | Not Started |  | Model endpoint / SDK | Mapped from 'Engineering' to Backend.
STORY-006 | EPIC-BE | Backend | Story | Rewrite existing model integration to call the DS model | Refactor or rewrite the current model integration layer so the production flow can call the DS-owned model interface. | DS model is invoked by the current application flow; legacy path replaced or feature-flagged. | High | Not Started |  | STORY-005 | Mapped from 'Engineering' to Backend.
STORY-007 | EPIC-PROD | Product | Story | Obtain MRM approval | Prepare and complete Model Risk Management approval activities required for rollout. | Required MRM artifacts submitted and approval status recorded. | High | Not Started |  | Model documentation, evaluation outputs
STORY-008 | EPIC-BE | Backend | Story | Meet non-functional requirements: fast search <1s and support 100 QPS | Design, implement, and validate the system to support fast search under 1 second and throughput of 100 QPS with the model. | Performance test report demonstrates <1s search latency and 100 QPS support in agreed conditions. | High | Not Started |  | Environment, load test plan | Captured as Backend implementation work; PMs can decide whether to split into separate performance stories.

## Lists
Story Type | Priority | Status | Epic ID | Epic Name
Story | High | Not Started | EPIC-DS | DS
Spike | Medium | In Progress | EPIC-BE | Backend
Task | Low | Blocked | EPIC-UI | UI
|  | Done | EPIC-PROD | Product
|  | On Hold | EPIC-DSX | DS Exploration