## Executive Summary
GenAI Email Theme Discovery Workbench — EPIC / JIRA Backlog
Purpose: create a PM-ready backlog for an email summarization, embedding, clustering, Gemini labeling, Dagster orchestration, and UI-based taxonomy review platform. MVP focuses on discovery, explainability, visual inspection, and maker/checker approval of Level 1 / Level 2 labels.
Metric | Value |  | Epic | Total Stories | MVP Stories
Total Stories | 43 |  | DS Exploration | 7 | 6
MVP Stories | 32 |  | DS | 10 | 9
Post-MVP Stories | 11 |  | Backend / Engineering | 10 | 7
P0 Stories | 32 |  | UI | 9 | 5
P1 Stories | 10 |  | Product / Governance | 7 | 5
P2 Stories | 1
Epics | 1
Epic | P0 | P1 | P2 | MVP %
DS Exploration | 6 | 1 | 0 | 85.71%
DS | 9 | 1 | 0 | 90%
Backend / Engineering | 7 | 3 | 0 | 70%
UI | 5 | 3 | 1 | 55.56%
Product / Governance | 5 | 2 | 0 | 71.43%

## JIRA Backlog
JIRA Key | Epic | Workstream | Story Title | User Story | Acceptance Criteria | Priority | Status | Owner | Dependencies | Deliverable / Artifact | Sprint | MVP Flag | Business Value | Notes
DSX-01 | DS Exploration | Data Discovery | Profile email dataset for clustering readiness | As a data scientist, I want to profile email subjects, bodies, threads, and communication metadata so that we understand data quality before clustering. | Dataset profile completed; duplicate emails, chains, signatures, and disclaimers identified; required fields documented. | P0 | Ready for Grooming | Data Science | Email sample dataset access | Data profiling report | Sprint 0 | MVP | Reduces data quality risk before DS investment
DSX-02 | DS Exploration | Embedding Strategy | Compare raw email vs structured summary embeddings | As a data scientist, I want to compare embeddings from raw email text versus Gemini-generated structured summaries so that we choose the best clustering input. | At least 3 embedding input strategies compared; sample clusters reviewed; recommendation documented. | P0 | Ready for Grooming | Data Science | DSX-01 | Embedding strategy comparison | Sprint 0 | MVP | Selects the right semantic representation for labels/themes
DSX-03 | DS Exploration | Clustering Baseline | Explore PCA + hierarchical clustering baseline | As a data scientist, I want to test PCA followed by agglomerative/hierarchical clustering so that we have an interpretable baseline taxonomy. | PCA dimensionality options tested; dendrogram generated; cluster quality metrics captured; representative clusters reviewed. | P0 | Ready for Grooming | Data Science | DSX-02 | Baseline clustering notebook | Sprint 1 | MVP | Creates explainable baseline for PM review
DSX-04 | DS Exploration | Visualization Prototype | Explore UMAP and t-SNE visualization for email clusters | As a product/data science team, we want UMAP and t-SNE views so that users can visually inspect cluster separation. | UMAP and t-SNE plots generated; clusters color-coded; hover metadata available in prototype; limitations documented. | P0 | Ready for Grooming | Data Science | DSX-02 | 2D visualization notebook | Sprint 1 | MVP | Improves business confidence in clustering output
DSX-05 | DS Exploration | Clustering Comparison | Explore density-based clustering with HDBSCAN/DBSCAN | As a data scientist, I want to test density-based clustering so that noisy/outlier emails are not forced into incorrect labels. | Density clustering tested; noise bucket identified; cluster size distribution captured; comparison documented. | P1 | Not Started | Data Science | DSX-02 | Density clustering comparison | Sprint 1 | Post-MVP | Identifies outliers and improves label purity | Prefer HDBSCAN where available; DBSCAN can be fallback.
DSX-06 | DS Exploration | Evaluation | Define cluster evaluation framework | As a product/data science team, we want objective and human-review metrics so that clustering quality can be measured before production. | Metrics include cluster coherence, silhouette/Davies-Bouldin where applicable, label consistency, business interpretability, and noise rate. | P0 | Ready for Grooming | Data Science | DSX-03, DSX-04 | Evaluation framework | Sprint 1 | MVP | Creates measurable MVP success criteria
DSX-07 | DS Exploration | Recommendation | Recommend final MVP clustering approach | As a product manager, I want a clear recommendation on the clustering approach so that the team can move from exploration to build. | Recommendation document completed with chosen algorithm, tradeoffs, risks, assumptions, and MVP scope. | P0 | Ready for Grooming | Product Manager | DSX-03, DSX-04, DSX-06 | MVP approach recommendation | Sprint 1 | MVP | Aligns PM, DS, and engineering on build direction
DS-01 | DS | Summarization | Define structured Gemini summary schema | As a data scientist, I want Gemini to produce structured summaries so that clustering inputs are consistent and less noisy. | JSON schema defined with summary, business intent, requested action, entities, urgency, risk, and evidence phrases. | P0 | Ready for Grooming | Data Science | DSX-01 | Structured summary schema | Sprint 1 | MVP | Creates standardized input for clustering and labeling
DS-02 | DS | Preprocessing | Build email cleaning and preprocessing logic | As a data scientist, I want to remove signatures, disclaimers, forwarded chains, and duplicate text so that summarization and embeddings are higher quality. | Cleaning logic implemented; before/after examples reviewed; exceptions logged. | P0 | Ready for Grooming | Data Science | DS-01 | Email preprocessing module | Sprint 1 | MVP | Improves summary and embedding quality
DS-03 | DS | Summarization | Generate Gemini structured summaries for email corpus | As a data scientist, I want to summarize email subject/body/thread content so that downstream clustering uses normalized business meaning. | Batch summarization job completed; JSON outputs persisted; failed records captured for retry. | P0 | Ready for Grooming | Data Science | DS-01, BE-05 | Structured summaries dataset | Sprint 2 | MVP | Transforms raw email noise into business meaning
DS-04 | DS | Embeddings | Generate embeddings from structured summaries | As a data scientist, I want embeddings from summary, intent, action, and entities so that similar emails can be grouped semantically. | Embeddings generated and stored; embedding model/version captured; input text template documented. | P0 | Ready for Grooming | Data Science | DS-03 | Embeddings dataset | Sprint 2 | MVP | Enables semantic grouping of emails
DS-05 | DS | Dimensionality Reduction | Build dimensionality reduction assets | As a data scientist, I want PCA/UMAP/t-SNE reduced representations so that clusters can be analyzed and visualized. | PCA vectors persisted for clustering; UMAP/t-SNE 2D coordinates persisted for UI. | P0 | Ready for Grooming | Data Science | DS-04 | PCA vectors and 2D coordinates | Sprint 2 | MVP | Feeds both clustering and UI visualization
DS-06 | DS | Clustering | Build clustering asset | As a data scientist, I want to run selected clustering algorithms so that emails are assigned to discovered theme groups. | Cluster IDs assigned; noise/outlier records handled; cluster metadata stored. | P0 | Ready for Grooming | Data Science | DS-05 | Cluster assignments | Sprint 2 | MVP | Produces initial discovered themes/classes
DS-07 | DS | Cluster Explanation | Select representative examples per cluster | As a data scientist, I want central and boundary examples from each cluster so that Gemini can label clusters using representative samples. | For each cluster, central examples, boundary examples, top terms, and neighboring clusters generated. | P0 | Ready for Grooming | Data Science | DS-06 | Cluster representative examples | Sprint 2 | MVP | Makes Gemini labeling more reliable and explainable
DS-08 | DS | LLM Labeling | Generate cluster labels using Gemini 2.5 Pro | As a product manager, I want Gemini to propose business-friendly Level 1 and Level 2 labels so that clusters can become usable taxonomy candidates. | Output includes Level 1 theme, Level 2 label, definition, inclusion/exclusion criteria, confidence, and merge/split recommendation. | P0 | Ready for Grooming | Data Science | DS-07, BE-05 | Gemini-generated taxonomy candidates | Sprint 3 | MVP | Converts clusters into PM-reviewable labels
DS-09 | DS | Taxonomy Versioning | Create taxonomy versioning logic | As a data scientist, I want each taxonomy run versioned so that approved labels can be compared across runs. | Taxonomy version ID created; cluster run, prompt version, model version, and reviewer status captured. | P1 | Not Started | Data Science | DS-08, BE-04 | Taxonomy versioning design | Sprint 3 | Post-MVP | Supports auditability and repeatable taxonomy refresh
DS-10 | DS | Reporting | Build cluster quality report | As a product manager, I want a report showing cluster quality and label confidence so that I can approve or reject the taxonomy. | Report includes cluster count, top clusters by volume, noise rate, confidence, sample emails, and human review status. | P0 | Ready for Grooming | Data Science | DS-08 | Cluster quality report | Sprint 3 | MVP | Helps PMs decide what to approve
BE-01 | Backend / Engineering | Dagster | Define Dagster asset graph for email clustering | As an engineer, I want each pipeline output modeled as a Dagster asset so that the workflow is observable and maintainable. | Assets defined for raw emails, cleaned emails, summaries, embeddings, dimensionality reduction, clusters, labels, and reports. | P0 | Ready for Grooming | Backend Engineering | DSX-07 | Dagster asset graph | Sprint 1 | MVP | Provides repeatable platform pipeline structure
BE-02 | Backend / Engineering | Dagster | Implement Dagster job for end-to-end clustering run | As an engineer, I want a Dagster job that runs the full discovery pipeline so that the process is repeatable. | Job executes end-to-end; failures visible; rerun from failed step supported. | P0 | Ready for Grooming | Backend Engineering | BE-01 | End-to-end Dagster job | Sprint 2 | MVP | Automates repeatable discovery runs
BE-03 | Backend / Engineering | Scheduling | Implement Dagster schedule or sensor trigger | As an engineer, I want the clustering job to run on demand and optionally on schedule/new data arrival so that PMs can refresh taxonomy. | Manual run supported; scheduled run configured; event-based sensor design documented if needed. | P1 | Not Started | Backend Engineering | BE-02 | Schedule/sensor configuration | Sprint 3 | Post-MVP | Enables recurring taxonomy refresh
BE-04 | Backend / Engineering | Persistence | Persist pipeline outputs with run IDs | As an engineer, I want all outputs stored with run IDs so that UI and audit users can retrieve historical clustering results. | Tables/files created for summaries, embeddings, clusters, labels, representative examples, and run metadata. | P0 | Ready for Grooming | Backend Engineering | BE-01 | Persistence model and storage implementation | Sprint 2 | MVP | Enables UI, audit, and repeatability
BE-05 | Backend / Engineering | LLM Service | Build Gemini invocation service wrapper | As an engineer, I want a standardized Gemini invocation wrapper so that prompts, schemas, retries, and errors are controlled. | Wrapper supports structured output, retry, timeout, logging, prompt version, and model version tracking. | P0 | Ready for Grooming | Backend Engineering | DS-01 | Gemini service wrapper | Sprint 2 | MVP | Controls LLM usage and operational reliability
BE-06 | Backend / Engineering | API | Build API to fetch cluster list | As a UI developer, I want an API that returns cluster summaries so that the UI can show all discovered themes. | API returns cluster ID, size, Level 1 label, Level 2 label, confidence, approval status, and top terms. | P0 | Ready for Grooming | Backend Engineering | BE-04, DS-08 | Cluster list API | Sprint 3 | MVP | Feeds cluster review UI
BE-07 | Backend / Engineering | API | Build API to fetch cluster details | As a UI developer, I want an API that returns details for a selected cluster so that users can inspect examples and definitions. | API returns central examples, boundary examples, representative summaries, Gemini label output, and nearby clusters. | P0 | Ready for Grooming | Backend Engineering | BE-06, DS-07 | Cluster detail API | Sprint 3 | MVP | Enables PM validation of each label
BE-08 | Backend / Engineering | Review Workflow | Build API to update label approval status | As a product manager, I want to approve, reject, edit, or merge labels so that the taxonomy becomes business-approved. | API supports approve, reject, edit label, merge cluster, split recommendation flag, and reviewer notes. | P0 | Ready for Grooming | Backend Engineering | BE-07, PROD-03 | Label review API | Sprint 3 | MVP | Enables maker/checker approval workflow
BE-09 | Backend / Engineering | Audit | Add audit and lineage tracking | As a control/governance user, I want lineage from email to summary to embedding to cluster to label so that the process is explainable. | Each label can be traced back to run ID, model version, prompt version, input records, and reviewer action. | P1 | Not Started | Platform Engineering | BE-04, BE-08 | Audit lineage model | Sprint 4 | Post-MVP | Supports governance and control review
BE-10 | Backend / Engineering | Monitoring | Add monitoring and error handling | As an engineer, I want pipeline-level monitoring so that failed Gemini calls, invalid JSON, and empty clusters are detected. | Error dashboard/logs available; retry queue created; failed records report generated. | P1 | Not Started | Platform Engineering | BE-02, BE-05 | Monitoring and error report | Sprint 4 | Post-MVP | Improves operational readiness
UI-01 | UI | Run Management | Build clustering run selection screen | As a product manager, I want to select a clustering run so that I can review the latest or prior taxonomy versions. | UI shows run date, dataset size, cluster count, noise rate, model version, and status. | P0 | Ready for Grooming | UI Engineering | BE-06 | Run selection screen | Sprint 3 | MVP | Allows PMs to start review workflow
UI-02 | UI | Visualization | Build UMAP/t-SNE cluster visualization | As a product manager, I want a 2D cluster map so that I can visually inspect email theme separation. | Scatter plot shows emails colored by cluster; hover shows subject/summary; filters available for cluster, label, confidence, and approval status. | P0 | Ready for Grooming | UI Engineering | BE-06, DS-05 | 2D cluster explorer | Sprint 3 | MVP | Makes clustering output understandable to business users
UI-03 | UI | Visualization | Build hierarchical clustering graph/dendrogram view | As a product manager, I want a hierarchy view so that I can understand Level 1 and Level 2 theme relationships. | Dendrogram or tree graph available; users can expand/collapse Level 1 and Level 2 groups. | P0 | Ready for Grooming | UI Engineering | BE-06, DS-08 | Hierarchical taxonomy view | Sprint 3 | MVP | Shows how clusters become a 2-level taxonomy
UI-04 | UI | Cluster Review | Build cluster detail page | As a product manager, I want to click a cluster and see its representative emails so that I can validate the proposed label. | Page shows cluster label, definition, central examples, boundary examples, top terms, size, and nearby clusters. | P0 | Ready for Grooming | UI Engineering | BE-07 | Cluster detail page | Sprint 3 | MVP | Supports informed label validation
UI-05 | UI | Approval Workflow | Build label review and approval workflow | As a product manager, I want to approve or edit Gemini-generated labels so that only reviewed taxonomy is promoted. | User can approve, reject, edit Level 1/Level 2 label, add notes, and submit decision. | P0 | Ready for Grooming | UI Engineering | BE-08, PROD-03 | Label approval screen | Sprint 4 | MVP | Creates PM-controlled taxonomy approval
UI-06 | UI | Taxonomy Refinement | Build merge/split recommendation view | As a product manager, I want to see clusters Gemini recommends merging or splitting so that the taxonomy is cleaner. | UI shows recommended merge/split candidates with rationale and supporting examples. | P1 | Not Started | UI Engineering | DS-08, BE-07 | Merge/split recommendation view | Sprint 4 | Post-MVP | Improves taxonomy quality over time
UI-07 | UI | Search | Build search and filter capability | As an operations user, I want to search emails, clusters, and labels so that I can quickly find themes of interest. | Search supports subject, summary, label, entity, cluster ID, and approval status. | P1 | Not Started | UI Engineering | BE-06, BE-07 | Search and filters | Sprint 4 | Post-MVP | Improves usability for reviewers
UI-08 | UI | Export | Build taxonomy export screen | As a product manager, I want to export approved labels so that the taxonomy can be shared with downstream classifier or governance teams. | Export available as CSV/JSON; includes label hierarchy, definition, inclusion/exclusion criteria, version, and approval metadata. | P1 | Not Started | UI Engineering | BE-08 | Taxonomy export screen | Sprint 4 | Post-MVP | Enables downstream classifier handoff
UI-09 | UI | Comparison | Build comparison view across clustering runs | As a product manager, I want to compare two taxonomy runs so that I can see whether labels are stable over time. | UI shows added/removed/changed clusters, label changes, cluster size changes, and stability indicators. | P2 | Not Started | UI Engineering | DS-09, BE-04 | Run comparison view | TBD | Post-MVP | Supports longer-term taxonomy governance
PROD-01 | Product / Governance | Objective | Define business objective for email theme discovery | As a product manager, I want the business goal clearly defined so that DS and engineering optimize for the right outcome. | Objective documented: theme discovery, routing labels, operational insights, classifier training taxonomy, or all of the above. | P0 | Ready for Grooming | Product Manager | None | Product objective statement | Sprint 0 | MVP | Aligns stakeholders on why this exists
PROD-02 | Product / Governance | Taxonomy Standards | Define Level 1 and Level 2 taxonomy standards | As a product manager, I want naming standards for themes/classes so that labels are consistent and business-friendly. | Naming standards documented with examples; Level 1 = broad theme, Level 2 = actionable class. | P0 | Ready for Grooming | Product Manager | PROD-01 | Taxonomy standards | Sprint 0 | MVP | Creates consistent labels for business use
PROD-03 | Product / Governance | Controls | Define review process for proposed labels | As a product manager, I want a maker/checker review process so that taxonomy labels are controlled before production use. | Reviewer roles defined; approval statuses defined; audit notes required for edits/rejections. | P0 | Ready for Grooming | Product Manager | PROD-02 | Label review workflow | Sprint 1 | MVP | Provides governance before production use
PROD-04 | Product / Governance | Label Definitions | Define inclusion and exclusion criteria standards | As a product manager, I want every label to include clear boundaries so that users know when to apply or not apply a class. | Every approved label has definition, inclusion criteria, exclusion criteria, and sample examples. | P0 | Ready for Grooming | Product Manager | PROD-02 | Label definition standards | Sprint 1 | MVP | Reduces ambiguity in email classification
PROD-05 | Product / Governance | Success Metrics | Define success metrics for MVP | As a product manager, I want measurable MVP success criteria so that the project can be evaluated objectively. | Success metrics include cluster interpretability, label approval rate, noise rate, coverage, reviewer satisfaction, and downstream usability. | P0 | Ready for Grooming | Product Manager | PROD-01 | MVP success metrics | Sprint 1 | MVP | Defines how success will be measured
PROD-06 | Product / Governance | Promotion Criteria | Define production promotion criteria | As a product manager, I want clear criteria for when a discovered taxonomy can be promoted to production classification. | Criteria documented: minimum review coverage, label stability, business approval, audit readiness, and fallback handling. | P1 | Not Started | Governance / Control | PROD-03, PROD-05 | Production promotion criteria | Sprint 4 | Post-MVP | Controls risk before production classification
PROD-07 | Product / Governance | Operating Model | Create taxonomy operating model | As a product manager, I want an operating model for ongoing taxonomy updates so that labels do not become stale. | Defines refresh cadence, owner, approval workflow, versioning, rollback, and communication process. | P1 | Not Started | Product Manager | PROD-06 | Taxonomy operating model | Sprint 4 | Post-MVP | Enables sustainable long-term governance

## MVP Scope
Phase | Recommended Stories | Outcome / Reason
Sprint 0 / Foundation | PROD-01, PROD-02, DSX-01, DSX-02 | Align business objective, define taxonomy standards, profile data, and select embedding strategy.
Sprint 1 / Exploration | DSX-03, DSX-04, DSX-06, DSX-07, DS-01, DS-02, BE-01, PROD-03, PROD-04, PROD-05 | Create clustering baseline, visualization prototype, summary schema, preprocessing logic, and governance guardrails.
Sprint 2 / Pipeline Build | DS-03, DS-04, DS-05, DS-06, DS-07, BE-02, BE-04, BE-05 | Run structured summarization, embeddings, dimensionality reduction, clustering, representative examples, and Dagster job.
Sprint 3 / Labeling + APIs | DS-08, DS-10, BE-06, BE-07, BE-08, UI-01, UI-02, UI-03, UI-04 | Generate Gemini labels and expose cluster list/detail APIs for PM review through cluster explorer UI.
Sprint 4 / Review MVP | UI-05 | Enable PM approval/edit/reject workflow for Gemini-generated Level 1 / Level 2 taxonomy labels.
Post-MVP | DSX-05, DS-09, BE-03, BE-09, BE-10, UI-06, UI-07, UI-08, UI-09, PROD-06, PROD-07 | Add density clustering, taxonomy versioning, scheduling, audit, monitoring, search/export, run comparison, promotion criteria, and operating model.

## Dagster Asset Map
Dagster Asset | Description | Owning Epic | Primary Stories | Output Consumers | MVP Flag
raw_email_corpus | Email subject/body/thread/communication metadata loaded for analysis. | Backend / Engineering | BE-01, BE-04 | cleaned_email_corpus | MVP
cleaned_email_corpus | Signatures, disclaimers, duplicate chains, and noisy text removed. | DS | DS-02 | gemini_structured_summaries | MVP
gemini_structured_summaries | Gemini-generated JSON summaries with business intent, action, entities, urgency, risk, and evidence. | DS | DS-01, DS-03, BE-05 | email_summary_embeddings | MVP
email_summary_embeddings | Embeddings created from summary + intent + action + entities. | DS | DS-04 | pca_embeddings, umap_coordinates, tsne_coordinates | MVP
pca_embeddings | Reduced-dimensional representation for clustering stability and performance. | DS | DS-05 | cluster_assignments | MVP
umap_coordinates | 2D coordinates for UI cluster explorer visualization. | DS / UI | DS-05, UI-02 | UI cluster map | MVP
tsne_coordinates | Alternative 2D visualization coordinates for comparison and visual validation. | DS / UI | DS-05, UI-02 | UI cluster map | MVP
cluster_assignments | Cluster IDs, sizes, and noise/outlier flags per email. | DS | DS-06 | cluster_representative_examples, UI | MVP
cluster_representative_examples | Central examples, boundary examples, top terms, and neighboring clusters. | DS | DS-07 | gemini_cluster_labels, UI cluster details | MVP
gemini_cluster_labels | Gemini-generated Level 1/Level 2 labels, definitions, inclusion/exclusion criteria, confidence, merge/split recommendations. | DS | DS-08 | taxonomy_review_dataset | MVP
cluster_quality_report | Cluster count, top clusters, noise rate, label confidence, and review readiness. | DS | DS-10 | PM review | MVP
taxonomy_review_dataset | PM reviewable dataset containing proposed labels and representative evidence. | Backend / UI | BE-06, BE-07, UI-04 | approved_taxonomy | MVP
approved_taxonomy | Human-reviewed and approved Level 1 / Level 2 taxonomy. | Product / Governance | PROD-03, UI-05, BE-08 | Downstream classifier / reporting | MVP
taxonomy_version_history | Historical taxonomy versions across runs with prompt/model/run lineage. | DS / Backend | DS-09, BE-09 | Run comparison / audit | Post-MVP
pipeline_monitoring_events | Dagster and LLM error events, invalid JSON, retries, and failed record reports. | Backend / Engineering | BE-10 | Operations dashboard | Post-MVP

## Category Lists
Epic | Priority | Status | Owner | MVP Flag | Sprint
DS Exploration | P0 | Not Started | Product Manager | MVP | Sprint 0
DS | P1 | Ready for Grooming | Data Science | Post-MVP | Sprint 1
Backend / Engineering | P2 | In Progress | Backend Engineering |  | Sprint 2
UI |  | Blocked | UI Engineering |  | Sprint 3
Product / Governance |  | Done | Platform Engineering |  | Sprint 4
|  |  | Governance / Control |  | TBD