## Summary
Agentic Workflow Platform Backlog Summary
Metric | Value | Epic Name | Story Count | Completed
Total Epics | 5 | DS | 7 | 0
Total Stories/Spikes | 23 | Backend | 5 | 0
High Priority Stories | 17 | UI | 3 | 0
|  | Product | 4 | 0
Notes | This workbook is a draft backlog structure for PM review. Stories can be resized, re-estimated, or split further during grooming. | DS Exploration | 4 | 0
Suggested Next Step | Review sequencing across DS foundation, Backend integrations, and UI authoring before sprint planning.
Products Referenced | EDGE Assist; EDGE Workbench
Standardization | Story title standardized to EDGE Assist where source input said EDGE Assiste.

## Epics
Agentic Workflow Platform - Draft Epics
Epic ID | Epic Name | Epic Description | Business Outcome | Suggested Owner | Priority | Status
EPIC-DS | DS | Build the core data science foundation for the agentic workflow platform, including ADK-based framework, ARC-configured runtime, YAML-driven configuration, evaluation hooks, and end-to-end workflows. | Enable a reusable, configurable agent platform for EDGE use cases. | DS Lead | High | Draft
EPIC-BE | Backend | Build the backend services and enterprise integrations required to power the platform, including MCP server, system connectors, and execution/configuration APIs. | Provide reliable platform connectivity and execution services. | Backend Lead | High | Draft
EPIC-UI | UI | Create the user interface for dynamic YAML-driven configuration, validation, and workflow operation. | Allow users to author and manage platform configuration through a usable interface. | UI Lead | Medium | Draft
EPIC-PROD | Product | Drive product planning, scoping, prioritization, stakeholder alignment, and release planning for the platform. | Ensure the initiative is well-scoped, measurable, and aligned with business needs. | Product Manager | High | Draft
EPIC-DSEXP | DS Exploration | Run spikes and exploratory tasks to de-risk architecture, runtime patterns, evaluation design, and enterprise integration approach. | Reduce implementation risk before full-scale build-out. | DS Architect | Medium | Draft

## Stories
Agentic Workflow Platform - Draft Stories and Spikes
Story ID | Epic ID | Epic Name | Story Title | Story Type | Description | Acceptance Criteria | Priority | Status | Suggested Owner | Dependencies | Notes
DS-001 | EPIC-DS | DS | Create base ADK framework with genai-common | Story | Establish the foundational Google ADK-based project structure integrated with genai-common so new agents and workflows can be built consistently. | Project skeleton, dependency structure, coding conventions, and reusable base components are available and reviewed. | High | Not Started | DS Lead |  | Core foundation story
DS-002 | EPIC-DS | DS | Create agent runtime configured with ARC | Story | Implement the agent runtime with ARC-based configuration so workflows can execute with consistent runtime controls and extensibility. | Runtime supports ARC configuration, environment setup, execution lifecycle, and basic observability hooks. | High | Not Started | DS Lead | DS-001
DS-003 | EPIC-DS | DS | Create YAML schema for templates, tools, workflows, prompts, and policy configs | Story | Define the configuration model for the platform using YAML-driven artifacts covering templates, tools, workflows, prompts, and policies. | Schema definitions are documented, versionable, and validated against representative examples. | High | Not Started | DS Team | DS-001
DS-004 | EPIC-DS | DS | Build config compiler and validator | Story | Create a compiler/validator that converts YAML configuration into runtime-ready platform objects and surfaces validation errors clearly. | Compiler can parse sample configs, fail fast on invalid definitions, and generate runtime-ready outputs. | High | Not Started | DS Team | DS-003
DS-005 | EPIC-DS | DS | Create evaluation hook | Story | Introduce evaluation hooks so agent runs can emit quality, trace, and feedback signals for future measurement and iteration. | Evaluation interface is implemented, sample metrics are captured, and hook points exist in runtime execution. | High | Not Started | DS Team | DS-002; DS-004
DS-006 | EPIC-DS | DS | Implement end-to-end agentic workflow for EDGE Assist | Story | Build the first end-to-end platform use case for EDGE Assist using the common framework, runtime, configs, and evaluation hooks. | Workflow runs successfully from config to execution with representative inputs and documented outputs. | High | Not Started | DS Team | DS-002; DS-004; DS-005; BE-001 | Standardized from 'EDGE Assiste'
DS-007 | EPIC-DS | DS | Implement end-to-end agentic workflow for EDGE Workbench | Story | Build the second end-to-end platform use case for EDGE Workbench to validate reuse across multiple products/workflows. | Workflow runs successfully and demonstrates reuse of platform components with minimal product-specific customization. | High | Not Started | DS Team | DS-002; DS-004; DS-005; BE-001
BE-001 | EPIC-BE | Backend | Create MCP server and base connection framework | Story | Build the core MCP server and common connection framework to support system integrations and tool exposure. | MCP server is available, connection lifecycle is defined, and sample connection path is tested. | High | Not Started | Backend Lead
BE-002 | EPIC-BE | Backend | Integrate R2D2 via MCP | Story | Implement the R2D2 connector and expose required capabilities through the MCP server. | R2D2 integration works in lower environment and core actions are callable from the platform. | High | Not Started | Backend Team | BE-001
BE-003 | EPIC-BE | Backend | Integrate Coin via MCP | Story | Implement the Coin connector and expose required capabilities through the MCP server. | Coin integration works in lower environment and core actions are callable from the platform. | High | Not Started | Backend Team | BE-001
BE-004 | EPIC-BE | Backend | Integrate Maas via MCP | Story | Implement the Maas connector and expose required capabilities through the MCP server. | Maas integration works in lower environment and core actions are callable from the platform. | High | Not Started | Backend Team | BE-001
BE-005 | EPIC-BE | Backend | Create backend APIs for config management and workflow execution | Story | Expose service APIs for configuration CRUD, compilation requests, and workflow execution/monitoring support. | APIs are documented, secured at baseline, and callable by UI and runtime components. | Medium | Not Started | Backend Team | BE-001; DS-004
UI-001 | EPIC-UI | UI | Build dynamic YAML config management UI | Story | Create a UI that allows users to create, edit, and manage YAML-based platform configurations dynamically. | Users can create and update core configuration artifacts through the UI and save them successfully. | High | Not Started | UI Lead | BE-005; DS-003
UI-002 | EPIC-UI | UI | Add config validation and preview experience | Story | Provide inline validation, compilation feedback, and preview support so users can confidently work with configurations. | Validation errors are surfaced clearly and users can preview compiled outputs or config summaries. | Medium | Not Started | UI Team | UI-001; DS-004
UI-003 | EPIC-UI | UI | Add workflow run and monitoring view | Story | Provide a user experience to launch supported workflows and review run status, outputs, and evaluation signals. | Users can trigger workflows, view run progress, and inspect basic run results from the UI. | Medium | Not Started | UI Team | UI-001; BE-005; DS-005
PROD-001 | EPIC-PROD | Product | Define platform vision, scope, and personas | Story | Document the platform problem statement, target personas, value proposition, and business scope. | Vision document and stakeholder-aligned scope statement are completed and reviewed. | High | Not Started | Product Manager
PROD-002 | EPIC-PROD | Product | Define MVP use cases and prioritization | Story | Identify and prioritize MVP workflows/features, including EDGE Assist and EDGE Workbench, based on business value and feasibility. | Prioritized MVP scope is agreed and linked to backlog sequencing. | High | Not Started | Product Manager | PROD-001
PROD-003 | EPIC-PROD | Product | Define success metrics, milestones, and NFRs | Story | Establish measurable success criteria, release milestones, and key non-functional requirements for the platform. | Success metrics, target milestones, and NFRs are documented and reviewed with engineering and DS leads. | High | Not Started | Product Manager | PROD-001
PROD-004 | EPIC-PROD | Product | Conduct stakeholder review and backlog sign-off | Story | Review the epic/story structure with key stakeholders and finalize backlog for implementation planning. | Backlog is reviewed, updated, and approved for execution planning. | Medium | Not Started | Product Manager | PROD-002; PROD-003
DSEXP-001 | EPIC-DSEXP | DS Exploration | Spike ADK plus genai-common platform fit | Spike | Evaluate how well Google ADK and genai-common support the target platform architecture and reusable development model. | Spike output includes recommendation, trade-offs, and proposed implementation approach. | High | Not Started | DS Architect
DSEXP-002 | EPIC-DSEXP | DS Exploration | Spike ARC runtime patterns and state model | Spike | Evaluate runtime patterns, state handling, and execution lifecycle options for ARC-based orchestration. | Spike output documents recommended runtime/state design and identified risks. | High | Not Started | DS Architect
DSEXP-003 | EPIC-DSEXP | DS Exploration | Spike evaluation framework and quality metrics | Spike | Explore evaluation options, run-level hooks, trace capture, and quality metrics for agent workflows. | Spike output recommends evaluation design, core metrics, and integration path. | Medium | Not Started | DS Architect
DSEXP-004 | EPIC-DSEXP | DS Exploration | Spike MCP integration pattern for enterprise systems | Spike | Evaluate the best pattern to expose and consume enterprise tools through MCP for systems such as R2D2, Coin, and Maas. | Spike output includes connector pattern recommendation and integration constraints. | Medium | Not Started | DS Architect

## Lists
Field | Value | Epic Names | Story Type
Priority | High | DS | Story
Priority | Medium | Backend | Spike
Priority | Low | UI
Status | Not Started | Product
Status | In Progress | DS Exploration
Status | Done